## Backlog
Sprint prio | PBI # | Title | Story | Definition of Done | Status | Dependencies
1 | 9 | MVE based on dev.kits | As a P.O, i want to have early feedback from relevant end-users, so that i can start prioratizing functionallity | MVP created: -Raspberry pie up and running with temperature development board -Account on IFTT setup so that when a resonable temp limit is reached, an email is sent to the user -5 pre-configured kits are sent to Early adopters | Done
2 | 1 | Report temperature | As an Early adopter given I have installed the system, I want to see the temperature in my greenhouse, so that my plants don’t die | This is done when: -Sensor reports temperature in Celsius to the processor -An average is calculated every minute | Done
3 | 3 | Email notifications | As an Early adopter given I have set the temperature limit, I want to be notified when it is too hot, so I can go and open the window | This is done when: -User can enter email in the device -User gets an email when outside the limit | Blocked
4 | 4 | Non-fuctional ID | As an Early adopter given I have installed the system, I want to have the system as a part of my natural greenhouse interior, So i can still have a beautiful greenhouse | This is done when: -5 Early adopters in the target group have seen a non functional mockup of the Greenhouse device While this is fullfilled: -There is reasonable area for a PCB | In sprint
5 | 6 | Temp sensor data | As a electronics developer Given i have software support I want to collect temperature data over time, so I can develop an intelligent filter | This is done when: -Dev boards for sensors has been hooked up to MCU -Unfiltered data is avalible on MCU debug port While this is fullfilled: -Sensor is easily avalible | In sprint
| 7 | Software toolchain | As a software developer Given i have a development board I want to know that i have enough interface and computation power, so I can develop peripheral drivers | This is done when: -Dev environment up -One peripheral and sensor delivering raw data on dev board While this is fullfilled: -Selected MCU has reasonable price -Selected MCU is easily avalible | Refined | Support from FAE:s of some major MCU manufacturers
| 8 | Select Cloud platform | As a backend developer, Given i have some knowledge of the expected loads I want early access to a relevant cloud platform, So i can prepare servers and architecture | This is done when: -Team has access to cloud platform -Some code are deployed from the development environment -A draft architecture is created that includes app, backend and device While this is fullfilled: -Servers are scalable in case of high load | Refined | Sourcing order cloud account
| 2 | Maximum Temperature notification | As an Early adopter given I have installed the system, I want to change the highest allowed temperature, So i can get notifications when its relevant for my selection of plants | This is done when: -User sets desired maximum temperature by using her mobile phone or computer -Limit is saved in the device -The user can see the current limit | Refined
| 5 |  | As a algorithm developer Given the user has accepted our EULA I want to collect temperature data over time, so I can develop an intelligent filter |  | Suggested | Legal to write EULA for first prototype series
| 10 |  |  |  | Suggested
| 11 |  |  |  | Suggested
| 12 |  |  |  | Suggested
| 13 |  |  |  | Suggested
| 14 |  |  |  | Suggested
| 15 |  |  |  | Suggested
| 16 |  |  |  | Suggested
| 17 |  |  |  | Suggested
| 18 |  |  |  | Suggested
| 19 |  |  |  | Suggested
| 20 |  |  |  | Suggested
| 21 |  |  |  | Suggested
| 22 |  |  |  | Suggested
| 23 |  |  |  | Suggested
| 24 |  |  |  | Suggested
| 25 |  |  |  | Suggested
| 26 |  |  |  | Suggested
| 27 |  |  |  | Suggested
| 28 |  |  |  | Suggested
| 29 |  |  |  | Suggested
| 30 |  |  |  | Suggested
| 31 |  |  |  | Suggested
| 32 |  |  |  | Suggested
| 33 |  |  |  | Suggested
| 34 |  |  |  | Suggested
| 35 |  |  |  | Suggested
| 36 |  |  |  | Suggested
Note on A1: Prio for the coming sprint. Empty means its inteded to be planned somewhere in the future
Note on B1: A running number to be able to tag tasks, code commits, documents etc.
Note on D1: Formulated as a user story, but the actor can be a team members since there in integrated systems are a lot of non-functional requiremnts and PBI:s tend to be more technical
Note on E1: Dev team helps with this. Since there are stories that might span several sprints, a simple way to handle this is to make DoD just fullfilling a part of the story. The next sprint a new PBI with the same Story, but a new DoD

## Competence avaliability
| Velocity: | 0.8
| Avalible hours | Estimated Hours | Workload
Electronics | 100 | 80 | 100%
Mobile application | 100 | 200 | 250%
Manufacturing | 60 | 30 | 62.5%
Mechanics | 100 | 110 | 137.5%
Device firmware | 100 | 250 | 312.5%
Backend/Frontend | 200 | 100 | 62.5%

## Dropdown
Status
Suggested
Refined
In sprint
Blocked
Done

## License
License page, do not remove
https://creativecommons.org/licenses/by-sa/4.0/
Created by Meqify (LinkedIn)